## All
SORT BY DATE
Workstream | Description | Due Date | Assigned to
Advertising / Program | Committee to review list of advertisers to help. | 2023-02-08 | All
Advertising / Program | Provide edits to program | 2023-04-17 | All
Printing and Signage | Identify signs / banners needed for this year | 2023-05-10 | All
Park Layout and Set up | Develop final map layout | 2023-06-14 | All

## Brad
SORT BY TASK
Workstream | Description | Due Date | Assigned to

## Gary
SORT BY TASK
Workstream | Description | Due Date | Assigned to
Advertising / Program | Update advertising package | 2023-01-01 | Gary
Advertising / Program | Present updated advertising proposal to committee | 2023-01-11 | Gary
Advertising / Program | Start selling advertising | 2023-01-12 | Gary
Advertising / Program | Send advertising packages to prior & others via email | 2023-02-15 | Gary
Advertising / Program | Collect art and payments from sponsors | 2023-03-10 | Gary
Advertising / Program | Get tshirt design for program | 2023-03-20 | Gary
Advertising / Program | Get band descriptions | 2023-03-27 | Gary
Advertising / Program | Art and payments - final due date | 2023-03-27 | Gary
Advertising / Program | Send art to Charlie McGuire (graphic designer) | 2023-03-27 | Gary
Advertising / Program | Develop draft of program | 2023-04-03 | Gary
Advertising / Program | Present draft program to committee | 2023-04-10 | Gary
Advertising / Program | Final program layout | 2023-04-18 | Gary
Advertising / Program | Send program to News Record for printing | 2023-04-19 | Gary
Advertising / Program | Pick up programs | 2023-05-13 | Gary

## Jamie
SORT BY TASK
Workstream | Description | Due Date | Assigned to
Adminstration | Apply for Mayfest | 2023-04-12 | Jamie
Merchandise | Identify possible designers | 2023-01-15 | Jamie
Merchandise | Select designers | 2023-02-05 | Jamie
Merchandise | Share design progress | 2023-02-19 | Jamie
Merchandise | Presentation of final designs | 2023-03-08 | Jamie
Merchandise | Assemble order & send to printer | 2023-03-27 | Jamie
Merchandise | Provide design to Program | 2023-03-31 | Jamie
Merchandise | Confirm colors, sizes and styles with printer | 2023-04-10 | Jamie
Merchandise | Submit order to printer | 2023-04-10 | Jamie
Merchandise | Order lawn signs | 2023-04-12 | Jamie
Merchandise | Expected tshirt arrival date | 2023-05-06 | Jamie
Merchandise | Shirt folding | 2023-05-07 | Jamie
Merchandise | Order any additional merch | 2023-06-08 | Jamie
Park Layout and Set up | Order port-a-johns | 2023-06-14 | Jamie
Printing and Signage | Provide tshirt design for all printing | 2023-04-12 | Jamie
Volunteers | Identify volunteers for Mayfest | 2023-05-07 | Jamie
Volunteers | Develop schedule for Mayfest | 2023-05-08 | Jamie
Volunteers | Identify volunteers for Duck Races | 2023-05-15 | Jamie and Katie
Volunteers | Develop Schedule for Duck Races | 2023-05-22 | Jamie
Volunteers | Determine schedule of sales for 2023 | 2023-05-24 | Jamie
Volunteers | Identify volunteers for street sales: (date) | 2023-06-01 | Jamie and Katie
Volunteers | Identify volunteers for street sales: (date) | 2023-06-01 | Jamie and Katie
Volunteers | Identify volunteers for street sales: (date) | 2023-06-01 | Jamie and Katie
Volunteers | Identify volunteers for street sales: (date) | 2023-06-01 | Jamie and Katie
Volunteers | Determine inventory of needed volunteers for the weekend | 2023-06-01 | Jamie and Katie
SORT BY DATE
Workstream | Description | Due Date | Assigned to
Merchandise | Identify possible designers | 2023-01-15 | Jamie
Merchandise | Select designers | 2023-02-05 | Jamie
Merchandise | Share design progress | 2023-02-19 | Jamie
Merchandise | Presentation of final designs | 2023-03-08 | Jamie
Merchandise | Assemble order & send to printer | 2023-03-27 | Jamie
Merchandise | Provide design to Program | 2023-03-31 | Jamie
Merchandise | Confirm colors, sizes and styles with printer | 2023-04-10 | Jamie
Merchandise | Submit order to printer | 2023-04-10 | Jamie
Adminstration | Apply for Mayfest | 2023-04-12 | Jamie
Merchandise | Order lawn signs | 2023-04-12 | Jamie
Printing and Signage | Provide tshirt design for all printing | 2023-04-12 | Jamie
Merchandise | Expected tshirt arrival date | 2023-05-06 | Jamie
Merchandise | Shirt folding | 2023-05-07 | Jamie
Volunteers | Identify volunteers for Mayfest | 2023-05-07 | Jamie
Volunteers | Develop schedule for Mayfest | 2023-05-08 | Jamie
Volunteers | Identify volunteers for Duck Races | 2023-05-15 | Jamie and Katie
Volunteers | Develop Schedule for Duck Races | 2023-05-22 | Jamie
Volunteers | Determine schedule of sales for 2023 | 2023-05-24 | Jamie
Volunteers | Identify volunteers for street sales: (date) | 2023-06-01 | Jamie and Katie
Volunteers | Identify volunteers for street sales: (date) | 2023-06-01 | Jamie and Katie
Volunteers | Identify volunteers for street sales: (date) | 2023-06-01 | Jamie and Katie
Volunteers | Identify volunteers for street sales: (date) | 2023-06-01 | Jamie and Katie
Volunteers | Determine inventory of needed volunteers for the weekend | 2023-06-01 | Jamie and Katie
Merchandise | Order any additional merch | 2023-06-08 | Jamie
Park Layout and Set up | Order port-a-johns | 2023-06-14 | Jamie

## Jim
SORT BY TASK
Workstream | Description | Due Date | Assigned to
Band Application & Selection | Launch band application on website | 2023-01-15 | Jim
Band Application & Selection | Close band applications on website | 2023-03-01 | Jim
Band Application & Selection | Create band summary doc | 2023-03-08 | Jim
Band Application & Selection | Zip MP3 files | 2023-03-08 | Jim
Band Application & Selection | Share summary and MP3 files with listening committee | 2023-03-08 | Jim
Merchandise | Post design to website | 2023-05-10 | Jim
Press | Initial press release with band announcement | 2023-05-01 | Jim
Printing and Signage | Inventory existing signs and banners | 2023-05-10 | Jim
Printing and Signage | Paint over old signs | 2023-06-14 | Jim
Printing and Signage | Signs for Deaf Area | 2023-06-24 | Jim
Volunteers | Contact Laurellie Jacobs for sign language interpreters | 2023-05-27 | Jim
Volunteers | Contact Tom and Marshia re stage banners | 2023-05-27 | Jim
Website Maintenance | Refresh maplewoodstock.com website with new info | 2023-01-11 | Jim
Website Maintenance | Update advertisers on website | 2023-01-11 | Jim
SORT BY DATE
Workstream | Description | Due Date | Assigned to
Website Maintenance | Refresh maplewoodstock.com website with new info | 2023-01-11 | Jim
Website Maintenance | Update advertisers on website | 2023-01-11 | Jim
Band Application & Selection | Launch band application on website | 2023-01-15 | Jim
Band Application & Selection | Close band applications on website | 2023-03-01 | Jim
Band Application & Selection | Create band summary doc | 2023-03-08 | Jim
Band Application & Selection | Zip MP3 files | 2023-03-08 | Jim
Band Application & Selection | Share summary and MP3 files with listening committee | 2023-03-08 | Jim
Press | Initial press release with band announcement | 2023-05-01 | Jim
Merchandise | Post design to website | 2023-05-10 | Jim
Printing and Signage | Inventory existing signs and banners | 2023-05-10 | Jim
Volunteers | Contact Laurellie Jacobs for sign language interpreters | 2023-05-27 | Jim
Volunteers | Contact Tom and Marshia re stage banners | 2023-05-27 | Jim
Printing and Signage | Paint over old signs | 2023-06-14 | Jim
Printing and Signage | Signs for Deaf Area | 2023-06-24 | Jim

## Katie
SORT BY TASK
Workstream | Description | Due Date | Assigned to
Arts Vendors | Email arts vendors from prior years | 2023-03-08 | Katie
Arts Vendors | Email possible vendors, identified during year | 2023-04-12 | Katie
Arts Vendors | Open arts vendor application on site | 2023-04-12 | Katie
Arts Vendors | Close arts vendor app on the site | 2023-05-29 | Katie
Arts Vendors | Arts vendor payments due | 2023-06-01 | Katie
Arts Vendors | Send contracts to vendors | 2023-06-10 | Katie
Arts Vendors | Assign prelim spaces | 2023-06-24 | Katie
Arts Vendors | Send liability forms | 2023-06-28 | Katie
Arts Vendors | Write thank you notes to arts vendors | 2023-07-16 | Katie
Beer Garden | Volunteer form to Elks | 2023-06-14 | Katie
Kids Zone | Contact zids zone vendor | 2023-03-01 | Katie
Kids Zone | Negotiate contract with vendor | 2023-04-01 | Katie / Tom
Kids Zone | Get ride sizes from vendor | 2023-06-01 | Katie
Park Layout and Set up | Determine number of arts and food vendors | 2023-04-12 | Katie
Park Layout and Set up | Determine prelim placement of Kids Zone | 2023-05-10 | Katie
Printing and Signage | Print Vendor Maps | 2023-06-24 | Katie / Susan
SORT BY DATE
Workstream | Description | Due Date | Assigned to
Kids Zone | Contact zids zone vendor | 2023-03-01 | Katie
Arts Vendors | Email arts vendors from prior years | 2023-03-08 | Katie
Kids Zone | Negotiate contract with vendor | 2023-04-01 | Katie / Tom
Arts Vendors | Email possible vendors, identified during year | 2023-04-12 | Katie
Arts Vendors | Open arts vendor application on site | 2023-04-12 | Katie
Park Layout and Set up | Determine number of arts and food vendors | 2023-04-12 | Katie
Park Layout and Set up | Determine prelim placement of Kids Zone | 2023-05-10 | Katie
Arts Vendors | Close arts vendor app on the site | 2023-05-29 | Katie
Arts Vendors | Arts vendor payments due | 2023-06-01 | Katie
Kids Zone | Get ride sizes from vendor | 2023-06-01 | Katie
Arts Vendors | Send contracts to vendors | 2023-06-10 | Katie
Beer Garden | Volunteer form to Elks | 2023-06-14 | Katie
Arts Vendors | Assign prelim spaces | 2023-06-24 | Katie
Printing and Signage | Print Vendor Maps | 2023-06-24 | Katie / Susan
Arts Vendors | Send liability forms | 2023-06-28 | Katie
Arts Vendors | Write thank you notes to arts vendors | 2023-07-16 | Katie

## Tarquin
SORT BY TASK
Workstream | Description | Due Date | Assigned to
Beer Garden | Confirm beer arrangement and vendors with Elks | 2023-05-10 | Tarquin
Beer Garden | Updare website with current beer vendors | 2023-06-14 | Tarquin
Headliners | Feedback from committee | 2023-01-15 | Tarquin
Headliners | Prelim decisions | 2023-02-01 | Tarquin
Headliners | Talk to agents on availability, cost, routing | 2023-02-08 | Tarquin
Headliners | Recirculate to the team | 2023-02-15 | Tarquin
Headliners | Get signed contracts from headliners | 2023-03-01 | Tarquin
Headliners | Review riders | 2023-04-01 | Tarquin
Headliners | Finalize riders | 2023-05-01 | Tarquin
Headliners | Provide rider details to production company | 2023-05-15 | Tarquin
Headliners | Review running list and agent recommendations | 2023-11-15 | Tarquin
Headliners | Develop list of top choices | 2023-12-01 | Tarquin
Headliners | Propose top choices with costs | 2023-12-01 | Tarquin
Printing and Signage | Print / laminate VIP Passes | 2023-06-24 | Tarquin
Production Company | Get pricing on stage, lights, front | 2023-04-01 | Tarquin
Production Company | Review headliner band riders | 2023-04-12 | Tarquin
Production Company | Agreement on headliner riders | 2023-04-12 | Tarquin
Production Company | Price backline with production company | 2023-05-10 | Tarquin
Production Company | Lock in the back line | 2023-06-08 | Tarquin
Production Company | Work with production co to reduce costs | 2023-06-14 | Tarquin
Production Company | Review proposal with road managers | 2023-06-14 | Tarquin
SORT BY DATE
Workstream | Description | Due Date | Assigned to
Headliners | Feedback from committee | 2023-01-15 | Tarquin
Headliners | Prelim decisions | 2023-02-01 | Tarquin
Headliners | Talk to agents on availability, cost, routing | 2023-02-08 | Tarquin
Headliners | Recirculate to the team | 2023-02-15 | Tarquin
Headliners | Get signed contracts from headliners | 2023-03-01 | Tarquin
Headliners | Review riders | 2023-04-01 | Tarquin
Production Company | Get pricing on stage, lights, front | 2023-04-01 | Tarquin
Production Company | Review headliner band riders | 2023-04-12 | Tarquin
Production Company | Agreement on headliner riders | 2023-04-12 | Tarquin
Headliners | Finalize riders | 2023-05-01 | Tarquin
Beer Garden | Confirm beer arrangement and vendors with Elks | 2023-05-10 | Tarquin
Production Company | Price backline with production company | 2023-05-10 | Tarquin
Headliners | Provide rider details to production company | 2023-05-15 | Tarquin
Production Company | Lock in the back line | 2023-06-08 | Tarquin
Beer Garden | Updare website with current beer vendors | 2023-06-14 | Tarquin
Production Company | Work with production co to reduce costs | 2023-06-14 | Tarquin
Production Company | Review proposal with road managers | 2023-06-14 | Tarquin
Printing and Signage | Print / laminate VIP Passes | 2023-06-24 | Tarquin
Headliners | Review running list and agent recommendations | 2023-11-15 | Tarquin
Headliners | Develop list of top choices | 2023-12-01 | Tarquin
Headliners | Propose top choices with costs | 2023-12-01 | Tarquin

## Susan
SORT BY TASK
Workstream | Description | Due Date | Assigned to
Park Layout and Set up | Obtain hand sanitzer and extra masks | 2023-06-14 | Susan
Printing and Signage | Order or make new signage | 2023-05-27 | Susan
Printing and Signage | Print Vehicle passes | 2023-06-24 | Susan
SORT BY DATE
Workstream | Description | Due Date | Assigned to
Printing and Signage | Order or make new signage | 2023-05-27 | Susan
Park Layout and Set up | Obtain hand sanitzer and extra masks | 2023-06-14 | Susan
Printing and Signage | Print Vehicle passes | 2023-06-24 | Susan

## Tom
SORT BY TASK
Workstream | Description | Due Date | Assigned to
Adminstration | Obtain approval for Beer Garden at Town Council meeting | 2023-03-08 | Tom
Adminstration | Schedule Dept Meeting with Town | 2023-03-08 | Tom
Adminstration | Department Head meeting | 2023-03-08 | Tom
Adminstration | File for Event Permit | 2023-04-12 | Tom
Adminstration | Apply for Liquor license for beer garden | 2023-04-12 | Tom
Adminstration | Town Council at Committee Meeting | 2023-04-12 | Tom
Adminstration | Schedule follow up meeting with Chief DuVaul | 2023-04-12 | Tom
Adminstration | Schedule follow up meeting with DPW | 2023-04-12 | Tom
Adminstration | Schedule follow up meetingwith MWFD | 2023-04-12 | Tom
Adminstration | Obtain event liability insurance | 2023-05-10 | Tom
Adminstration | Reach out to SOMA Two Towns re: Senior Tent | 2023-06-14 | Tom
Adminstration | Reach out to Laurellie to confirm | 2023-06-14 | Tom
Band Application & Selection | Schedule listening committee meeting | 2023-02-23 | Tom
Band Application & Selection | Determine number of band slots, based on headliners | 2023-03-01 | Tom
Band Application & Selection | Hold listening committee meeting | 2023-03-18 | Tom
Band Application & Selection | Complete band decisions | 2023-03-19 | Tom
Band Application & Selection | Build band schedule | 2023-03-19 | Tom
Band Application & Selection | Send congratulation letters | 2023-03-19 | Tom
Band Application & Selection | Send "thank you for applying" letters | 2023-03-19 | Tom
Band Application & Selection | Band responses due | 2023-03-26 | Tom
Band Application & Selection | Local bands confirmed | 2023-03-27 | Tom
Band Application & Selection | Collect band info for press release and program | 2023-04-30 | Tom
Band Application & Selection | Send "save the date" email for the band meeting | 2023-05-15 | Tom
Band Application & Selection | Band meeting | 2023-06-15 | Tom
Band Application & Selection | Receive lyrics from bands for interpreters | 2023-06-28 | Tom
Budget | Fiscal year | 2023-01-11 | Tom
Budget | Set prelim budget | 2023-01-11 | Tom
Budget | Set budget for bands | 2023-03-08 | Tom
Budget | Set final budget | 2023-03-08 | Tom
Budget | Issue public appeal for funds | 2023-06-14 | Tom
Park Layout and Set up | Determine general park layout | 2023-04-12 | Tom
Production Company | Every 3 years, put event out to bid | 2023-01-01 | Tom
Production Company | Compare bids | 2023-04-01 | Tom
SORT BY DATE
Workstream | Description | Due Date | Assigned to
Production Company | Every 3 years, put event out to bid | 2023-01-01 | Tom
Budget | Fiscal year | 2023-01-11 | Tom
Budget | Set prelim budget | 2023-01-11 | Tom
Band Application & Selection | Schedule listening committee meeting | 2023-02-23 | Tom
Band Application & Selection | Determine number of band slots, based on headliners | 2023-03-01 | Tom
Adminstration | Obtain approval for Beer Garden at Town Council meeting | 2023-03-08 | Tom
Adminstration | Schedule Dept Meeting with Town | 2023-03-08 | Tom
Adminstration | Department Head meeting | 2023-03-08 | Tom
Budget | Set budget for bands | 2023-03-08 | Tom
Budget | Set final budget | 2023-03-08 | Tom
Band Application & Selection | Hold listening committee meeting | 2023-03-18 | Tom
Band Application & Selection | Complete band decisions | 2023-03-19 | Tom
Band Application & Selection | Build band schedule | 2023-03-19 | Tom
Band Application & Selection | Send congratulation letters | 2023-03-19 | Tom
Band Application & Selection | Send "thank you for applying" letters | 2023-03-19 | Tom
Band Application & Selection | Band responses due | 2023-03-26 | Tom
Band Application & Selection | Local bands confirmed | 2023-03-27 | Tom
Production Company | Compare bids | 2023-04-01 | Tom
Adminstration | File for Event Permit | 2023-04-12 | Tom
Adminstration | Apply for Liquor license for beer garden | 2023-04-12 | Tom
Adminstration | Town Council at Committee Meeting | 2023-04-12 | Tom
Adminstration | Schedule follow up meeting with Chief DuVaul | 2023-04-12 | Tom
Adminstration | Schedule follow up meeting with DPW | 2023-04-12 | Tom
Adminstration | Schedule follow up meetingwith MWFD | 2023-04-12 | Tom
Park Layout and Set up | Determine general park layout | 2023-04-12 | Tom
Band Application & Selection | Collect band info for press release and program | 2023-04-30 | Tom
Adminstration | Obtain event liability insurance | 2023-05-10 | Tom
Band Application & Selection | Send "save the date" email for the band meeting | 2023-05-15 | Tom
Adminstration | Reach out to SOMA Two Towns re: Senior Tent | 2023-06-14 | Tom
Adminstration | Reach out to Laurellie to confirm | 2023-06-14 | Tom
Budget | Issue public appeal for funds | 2023-06-14 | Tom
Band Application & Selection | Band meeting | 2023-06-15 | Tom
Band Application & Selection | Receive lyrics from bands for interpreters | 2023-06-28 | Tom